## Tasks
Things to Do | Solution | Person
Time format (Reader)
Time format (Writer)
Reader + Writer: Null values should be allowed for QvxSpecialExtent, LocalDateTime, LocalDate, etc.
Writer: Support for LocalDateTime, LocalDate, etc cell types
Any dates before Feb 28, 1900 are one day off
Money: 2 decimals in KNIME (write as double), write Money in Qvx
Preprocessing (convert doubles to integers, or vice versa)
Date-time (even if not specified as date, use regular expressions)
Read qvx files directly from the internet |  | Matt | Tuesday
Deal with missing cells (esp. with dates from strings,and verify nothing else was broken by this) | Establish and run test cases | Matt | Saturday
Finalized code clean-up (Tuesday) |  | Matt | Tuesday
Post JAXB code to Github
Fix AM / PM Problem |  | Matt | ?
Regular expression fix
Double check that FixPt Decimals still works |  | Matt | Tuesday